## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
1 | Sign In | Authentication | Simple | Allows registered users to log into the system using their email and password. | Iteration 3 | Doing
2 | Sign Out | Authentication | Simple | Logs the user out and terminates the active session. | Iteration 3 | Doing
3 | Registration | Authentication | Medium | Enables new users to create an account by providing basic credentials like email, password, and phone number. | Iteration 3 | Doing
4 | Password Recovery | Authentication | Medium | Allows users to reset their password through a verification process, typically via email. | Iteration 3 | Doing
5 | Role-Based Access Control | User Management | Medium | Assigns users to specific roles (Customer, Admin, Restaurant Owner, Staff), each with tailored access permissions and feature visibility. | Iteration 3 | Doing
6 | User Session Management | User Management | Medium | Maintains login sessions via cookies or tokens, keeping users authenticated across their interaction with the platform. | Iteration 3 | Doing
7 | User Profile Management | User Management | Medium | Users can update their personal details (name, email, phone number) and view their food suggestion and order history. | Iteration 3 | Doing
8 | Mood & Preference Detection | Food Suggestion | Complex | Uses GenAI to interpret user emotions and preferences from natural language inputs (e.g., "I feel cold and want something spicy") to suggest suitable dishes. | Iteration 3 | Doing
9 | One-Click Smart Suggestion | Food Suggestion | Medium | Instantly recommends food based on user history, time of day, location, or weather context. | Iteration 3 | Doing
10 | Random Food Wheel (Manual Input) | Food Suggestion | Medium | Allows users to enter custom food options into a spinning wheel to randomly select a meal. | Iteration 3 | Doing
11 | Random Food Wheel (AI Preset) | Food Suggestion | Complex | Uses AI-generated food options in a spinning wheel for spontaneous and personalized suggestions. | Iteration 3 | Doing
12 | Food History Log (Wheel) | Food Suggestion | Medium | Tracks the outcome of each spin from the food wheel and stores it in the user’s history. | Iteration 3 | Doing
13 | Display Food Suggestions | Food Suggestion | Medium | Presents detailed food recommendations with visuals, descriptions, and options to book or pre-order. | Iteration 3 | Doing
14 | Guided Suggestion Flow | Food Suggestion | Complex | Engages users through a question-based interface where GenAI interprets responses to recommend personalized meals. | Iteration 3 | Doing
15 | Food Preview Updates | Food Suggestion | Medium | Dynamically updates food images and details in real time based on user inputs during suggestion flow. | Iteration 3 | Doing
16 | Payment Gateway Integration | Payment and Transaction Management | Complex | Secure integration with payment providers (e.g., Stripe, PayPal) to process payments. | Iteration 3 | Doing
17 | Payment Validation | Payment and Transaction Management | Medium | Verifies payment transactions and confirms bookings only upon successful completion. | Iteration 3 | Doing
18 | Payment History | Payment and Transaction Management | Medium | Displays a user’s full history of payments, with downloadable invoices. | Iteration 3 | Doing
19 | Refund Functionality | Payment and Transaction Management | Medium | Allows processing of refunds in cases of booking or order cancellations. | Iteration 3 | Doing
20 | Invoice Generation | Payment and Transaction Management | Medium | Automatically generates invoices for each transaction, accessible from the user’s account. | Iteration 3 | Doing
21 | Restaurant Details View | Restaurant Management | Simple | Displays comprehensive restaurant profiles including images, contact details, and location. | Iteration 3 | Doing
22 | Restaurant Profile Management | Restaurant Management | Medium | Restaurant owners can manage and update their establishment’s public information. | Iteration 3 | Doing
23 | Restaurant Menu Management | Restaurant Management | Medium | Restaurants can add, modify, or remove dishes from their menu. | Iteration 3 | Doing
24 | Food Item Editing | Restaurant Management | Simple | Edit dish details such as name, description, price, and availability. | Iteration 3 | Doing
25 | Food Categorization | Restaurant Management | Medium | Organize food items into logical categories (e.g., appetizers, main course, desserts). | Iteration 3 | Doing
26 | Restaurant Location Display | Restaurant Management | Simple | Embedded Google Maps display the restaurant’s location. | Iteration 3 | Doing
27 | Navigation & Directions | Restaurant Management | Medium | Users can click to open Google Maps with directions to the restaurant from their current location. | Iteration 3 | Doing
28 | Ad Creation by Restaurant | Advertisement and Marketing | Medium | Restaurant owners can design ads with images and descriptions to promote their services. | Iteration 3 | Doing
29 | Ad Payment Tracking | Advertisement and Marketing | Medium | Track payment status for restaurant advertisements. | Iteration 3 | Doing
30 | Ad Display on Homepage | Advertisement and Marketing | Simple | Ads appear on the homepage to attract customer attention. | Iteration 3 | Doing
31 | Ad Management by Admin | Advertisement and Marketing | Medium | Admins can moderate, remove, or prioritize ads based on performance and compliance. | Iteration 3 | Doing
32 | Ad Performance Analytics | Advertisement and Marketing | Complex | Admins view metrics to evaluate ad performance and make strategic decisions. | Iteration 3 | Doing
33 | Manage Restaurant Availability | Booking and Ordering | Medium | Restaurants define and update available time slots for reservations and pre-orders. | Iteration 3 | Doing
34 | Booking System | Booking and Ordering | Medium | Enables users to book a table at a selected restaurant. | Iteration 3 | Done
35 | Booking Time Selection | Booking and Ordering | Simple | Users can pick a specific time slot from the available options for their reservation. | Iteration 3 | Doing
36 | Pre-Order System | Booking and Ordering | Medium | Users can pre-order meals tied to a specific booking (not for home delivery). | Iteration 3 | Doing
37 | User Feedback System | User Interaction and Feedback | Medium | Users can rate restaurants and leave detailed comments based on their experience. | Iteration 3 | Doing
38 | Feedback Moderation | User Interaction and Feedback | Medium | Admins can moderate or remove inappropriate or unhelpful reviews. | Iteration 3 | Doing
39 | Push Notifications | User Interaction and Feedback | Medium | Real-time alerts for bookings, orders, promotions, or important system updates. | Iteration 3 | Doing
40 | Send Notifications for Bookings/Orders | User Interaction and Feedback | Simple | Specific notifications are triggered for booking confirmations or order status updates. | Iteration 3 | Doing

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | Employer payment gateway errors | Medium | Medium | ThangNT | 2025-03-20 |  | Open | PayOS API integration failed
2 | Admin dashboard slow loading | Low | Medium | DatTV | 2025-04-10 |  | Open | Database query optimization needed
3 | Job application submissions failing | High | High | HuyPN | 2025-03-05 | 2025-03-15 | Closed | Can connect with CV featured to apply
4 | Email notifications not sent | Medium | Medium | NiTNH | 2025-03-20 | 2025-03-21 | Closed
5 | Real-time notifications not sent | High | High | DatTV | 2025-03-20 | 2025-03-22 | Closed | SignalR cannot connect with frontend
6 | Search filters returning wrong results | Medium | Medium | ThanhTT | 2025-03-08 | 2025-03-18 | Closed | Missing parameters to query
7 | Candidate resume download failure | Medium | Medium | HuyPN | 2025-03-07 | 2025-03-08 | Closed | PDF generation library compatibility issue

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
2025-03-05 | "Application status not updating" | HuyPN | Low | Cancelled
2025-03-10 | Quản lý đơn ứng tuyển, trạng thái chờ duyệt, mời pv,... như thế nào | ThangNT | Medium | Closed | List danh sách applied theo từng Job, candidate được approve sẽ có thể mời phỏng vấn
2025-03-15 | Không có nút unFeatured hay sao | DatTV | Low |  | Không cần thiết
2025-04-15 | Trong trường hợp CV đã apply vào 1 job bất kỳ, trong quá trình đó mà candidate sửa cv thì cv đã apply ở chỗ sẽ bị thay đổi theo vì (mình truy vấn thông tin từ DB) | ThangNT | High | Closed | Khi update CV check nếu mà CV có apply vào 1 job nào đó thì sẽ clone ra 1 CV mới để update (CV mới sẽ có ID mới) ẩn feature nếu đang feature và chueyẻn trạng thái feature sang cho CV mới clone ra
2025-04-16 | Đã đọc được data ở CV PDF dạng hình ảnh chưa? | DatTV | High | Open | Có thể đưa ra hướng giải quyết là nhờ AI lọc ra những trường đưa vào DB
2025-04-20 | Candidate bị Reject CV rồi thì có được apply lại không ? | ThangNT | Medium | Closed | cho phép 3 lần apply mỗi Job
2025-04-20 | Candidate muốn rút đơn Apply | DatTV | Medium | Closed | Check trường hợp nếu chưa review application có quyền rút (tức là đang pending)
2025-04-20 | Làm thế nào để ứng viên k nộp đơn trùng nhiều lần cho 1 job | DatTV | Medium | Closed | Nếu đã nộp mà trong trạng thái pending sẽ không được apply nữa, còn nếu reject có quyền apply lại theo số lần quy định
2025-03-10 | Trường hợp toàn bộ đều là employer, làm thế nào để biết employer nào là uy tín, k phải phá hệ thống | ThangNT | High | Closed | Hệ thống đã thêm chức năng xác thực employer thông qua mã số thuế và giấy phép kinh doanh
2025-03-06 | Quy trình tuyển dụng là tự động hay thủ công ? | HuyPN | Low | Closed | Thủ Công
2025-03-16 | Có tạo được format để candidate tạo CV không | HuyPN | Medium | Closed | Tạo được format theo nhiều ngành nghề từ hệ thống
2025-03-16 | Tìm kiếm với từ khóa phức tạo được không | DatTV | Medium | Closed | Candidate hay Employer đều có thể nâng cấp tài khoản đê có thể sử dụng nhiều chức năng hấp dẫn hơn, ví dụ như AI
2025-03-16 | Xem lại kỹ phần dòng tiền nâng cấp gói | ThangNT | Low | Closed | Tích họp bên thứ 3 để thực hiện chức năng thanh toán, và lưu những thông tin đó vào database để có thể dễ quản lý
2025-03-20 | Hiện tại, nhóm mới chỉ filter job theo ngành CNTT (IT), trong khi đề tài không giới hạn ngành nghề cụ thể. Cần mở rộng danh mục ngành nghề, ví dụ: Kinh doanh - Marketing, tài chính - Kế toán, thiết kế đồ họa, dịch vụ khách hàng, ... Thực hiện lọc đa ngành nghề để đảm bảo tính bao quát của hệ thống. | HuyPN | High | Closed | Tạo được format theo nhiều ngành nghề từ hệ thống
2025-03-16 | Sequence Diagram: Bổ sung lifeline: Mỗi đối tượng trong Sequence Diagram cần có dòng thời gian (lifeline) để thể hiện thời điểm chúng tồn tại hoặc bị hủy. Chưa có toán tử tương tác (alt) cho if-else: Cần sử dụng alt để thể hiện nhánh điều kiện (ví dụ: Nếu ứng viên phù hợp thì hiển thị đề xuất, ngược lại không hiển thị) | NiTNH | Medium | Closed | Đã update toàn bộ sequence diagram ở report, đầy đủ các yêu cầu
2025-03-16 | Cần thống nhất cách hiển thị số tiền lương và các giao dịch tài chính theo chuẩn quốc tế hoặc chuẩn địa phương. | ThangNT | Low | Closed | Đã thống nhất cách hiển thị tiền trên hệ thống là sử dụng ToLocaleString, để chuyển thành VND
2025-03-28 | Nhà tuyển dụng có thể cấu hình bật/tắt thông báo trong phần cài đặt tài khoản. | DatTV | Low | Closed | Đã có chức năng cho người dùng tùy ý bật tắt thông báo theo tùy thích
2025-03-18 | Hệ thống cần hỗ trợ Realtime Notification khi: Nhà tuyển dụng nhận được ứng viên mới. Ứng viên nhận được phản hồi từ employer. | DatTV | Medium | Closed | Hệ thống realtime hoạt động đúng thời gian thực, đảm bảo cho người dùng nhận thông báo ngay tức khắc, không bị chậm trễ bất cứ thông tin nào liên quan trực tiếp đến người dùng
2025-04-03 | Ứng dụng AI để phân tích ứng viên phù hợp. Nếu đã có mô hình AI thì cần trình bày rõ logic lọc và output. | HuyPN | High | Closed | Hệ thống đã tích hợp Cohere và OpenAI để thực hiện chức năng đề xuất job hoặc là cv dựa trên những yêu cầu từ employer hay là candidate, đã trình bày logic collect data và query data ở silde thuyết trình
2025-04-18 | Làm sao để đảm bảo ứng viên không nộp đơn trùng nhiều lần cho cùng một công việc | DatTV | Medium | Closed | Hệ thống đã cập nhập 1 candidate chỉ có thể apply vào 1 job tối đa 3 lần, nếu bị từ chối cả 3 lần thì k được request để apply vào job đó nữa
2025-04-18 | Cho phép ứng viên rút hồ sơ (withdraw) trước khi nhà tuyển dụng duyệt sẽ tăng trải nghiệm người dùng và giảm gánh nặng cho nhà tuyển dụng. Nếu đã duyệt rồi thì có thể khóa quyền rút lại. | DatTV | Medium | Closed | Candidate apply nhưng đang trong trạng thái pending, có thể thực hiện rút cv lại nếu cần chỉnh sửa hoặc cập nhật cv cho phù hợp, sau đó có thể nộp lại
2025-02-28 | Có lịch sử trạng thái đơn ứng tuyển không (đã duyệt, từ chối, đang chờ...)? | ThanhTT | Medium | Closed | Bảng lịch sử trạng thái đơn ứng tuyển của 1 candidate (có thể theo kiểu timeline) giúp nhà tuyển dụng dễ theo dõi.
2025-03-20 | Gợi ý nâng cao nếu còn thời gian: Thêm phân tích dữ liệu ứng viên: độ tương thích, phân tích từ khóa kỹ năng. | DatTV | Medium | Closed | Hệ thống sử dụng Cohere để có thể phân tích kỹ năng từ cv của người dùng, sau đó dùng các thuật toán như mã hóa thông tin thành 1 vector, sau đó lưu vào db, rồi sử dụng công thức tính toán để có thể tính ra độ tương thích giữa cv và job, sau đó đề xuất cho candidate job tương ứng, độ tương thích cao
2025-04-14 | Hỗ trợ đánh giá, phản hồi sau phỏng vấn. Thống kê báo cáo cho admin: lượt ứng tuyển, tỷ lệ chấp nhận, số job đang mở. | HuyPN | Medium | Closed | Hệ thống đã có chức năng report job, nếu job vi phạm hợp đồng hay gì đó